## Jeffrey Qua
Work Allocation Hours
Member: | Jeffrey Qua
Date (dd/mm/yyyy) | Hours | Activity
2006-01-18 | 2 | Website
2006-01-19 | 3 | Website
2006-01-20 | 4 | Website
2006-01-21 | 2 | Autism Research
2006-01-24 | 2 | Client Meeting & TA Meeting
2006-01-26 | 1 | Website
| 1 | SRS
Week #1: | 15
2006-01-30 | 4 | SRS
2006-01-31 | 1 | TA Meeting
| 3 | SRS
2006-02-01 | 4 | SRS / Project
2006-02-02 | 2 | Project
| 1 | SRS
Week #2: | 15
2006-02-07 | 1.5 | TA Meeting
2006-02-08 | 2 | SRS
2006-02-09 | 2.5 | SRS
| 3 | Project Plan
Week #3: | 9
2006-02-12 | 0.5 | Website
2006-02-14 | 1 | SDD
2006-02-15 | 1.5 | SDD
| 2 | SDD
2006-02-16 | 2 | Group Meeting
Week #4 | 7
2006-02-21 | 1.5 | TA Meeting
2006-02-22 | 1 | Group Meeting
| 3 | SDD
2006-02-24 | 1 | SDD
Week #5 | 6.5
2006-02-28 | 1.5 | TA Meeting
2006-03-02 | 3 | Implementation
2006-03-04 | 1 | Implementation
Week #6 | 5.5
2006-03-05 | 4 | Implementation
2006-03-07 | 1.5 | TA Meeting
2006-03-08 | 1 | graphics & logo design
2006-03-09 | 2 | graphics & logo design
2006-03-10 | 2 | graphics & logo design
2006-03-11 | 1 | graphics & logo design
| 2 | management
Week #7 | 13.5
2206-03-12 | 2 | graphics & logo design
2006-03-14 | 2 | filming
| 0.5 | TA Meeting
| 0.5 | test plan - section 3
| 2.5 | audio
2006-03-16 | 1 | test plan - section 3
| 3.5 | SDS - diagrams
| 0.5 | video encoding
2006-03-17 | 1.5 | SRS editing
Week #8 | 14
2006-03-19 | 2.5 | TA + Group meeting
~ | 13
2006-03-25
Week #8 | 15.5
2006-03-19 | 2.5 | TA + Group meeting
~ | 13 | management
2006-03-25
Week #9 | 15.5
2006-03-26 | 5 | TA + Group meeting
~ | 13 | user manual
2006-04-01
Week #10 | 18 |  | Total: | 134.5

## Ian Cook
Work Allocation Hours
Member: | Ian Cook
Date (dd/mm/yyyy) | Hours | Activity
2006-01-24 | 2 | Client Meeting & TA Meeting
Week #1: | 2
2006-01-31 | 1 | SRS section 3.5
| 1 | TA Meeting
2006-01-02 | 1 | setting up eclipse & CVS
2006-02-02 | 3 | SRS section 3.5, setting up eclipse & CVS
Week #2: | 5
2006-02-07 | 1.5 | TA Meeting
2006-02-08 | 5 | SRS section 3.5 (revision)
2006-02-09 | 1 | setting up eclipse & CVS
Week #3: | 7.5
2006-02-15 | 2 | SDD 3
2006-02-16 | 2 | Group Meeting
2006-02-18 | 8 | SDD 5 - class diagram description
Week #4 | 12
2006-02-21 | 1.5 | TA Meeting
2006-02-23 | 1 | SDD 3 - revision
2006-02-24 | 1 | XML parser
Week #5 | 3.5
2006-02-28 | 1.5 | TA Meeting
2006-03-01 | 2.5 | Video Shooting
2006-03-04 | 5 | XML parser
Week #6 | 9
2006-03-07 | 1.5 | TA Meeting
2006-03-09 | 2.5 | filiming
| 5 | XML parser
Week #7 | 9
2006-03-14 | 2 | filming
| 0.5 | TA Meeting
2006-03-15 | 8 | CVS & testing
2006-03-18 | 14 | CVS & testing
Week #8 | 24.5
2006-03-19 | 2.5 | TA + Group meeting
~ | 30 | dealing with issues on mac
2006-03-25
Week #9 | 32.5
2006-03-26 | 5 | TA + Group meeting
~ | 30 | dealing with issues on mac
2006-04-01
Week #10 | 35 |  | Total | 140

## Michael Tien
Work Allocation Hours
Member: | Michael Tien
Date (dd/mm/yyyy) | Hours | Activity
2006-01-24 | 2 | Client Meeting & TA Meeting
Week #1: | 2
2006-01-31 | 2 | SRS 3.3 - 3.4 (first draft)
| 1 | TA Meeting
2006-02-01 | 2 | SRS 3.3 - 3.4
2006-02-02 | 2 | SRS 4 & Test plan
| 0.5 | Work Allocation Hours
Week #2: | 7.5
2006-02-07 | 2 | Product logo
| 1.5 | TA Meeting
2006-02-08 | 2 | SRS 3.3 - 3.4 revise
2006-02-09 | 1 | Project Plan 4.2
Week #3: | 6.5
2006-02-15 | 1 | SDD 3
2006-02-16 | 2 | Group Meeting
| 1 | SDD 3
2006-02-18 | 3 | SDD 5 - Sequence Diagram
2006-02-19 | 10 | SDD 5 - Sequence Diagram
Week #4 | 17
2006-02-21 | 1.5 | TA Meeting
2006-02-23 | 2 | SDD 5 - Sequence Diagram (revise)
2006-02-24 | 4 | SDD 5 - Sequence Diagram (revise)
Week #5 | 7.5
2006-02-28 | 1.5 | TA Meeting
2006-03-01 | 2.5 | Video Shooting
2006-03-02 | 5 | Video Editing
2006-03-04 | 1 | JMF Video Player Research
Week #6 | 10
2006-03-07 | 1.5 | TA Meeting
2006-03-09 | 2.5 | filiming
2006-03-10 | 5 | video editing
2006-03-11 | 2 | testing
| 7 | test plan outline
Week #7 | 18
2006-03-14 | 2 | filming
| 0.5 | TA Meeting
| 2 | Video Editing
2006-03-15 | 8 | CVS & testing
2006-03-17 | 2 | SDS - sequence diagrams
2006-03-18 | 14 | CVS & testing
Week #8 | 28.5
2006-03-19 | 2.5 | TA + Group meeting
~ | 10 | Unit test/System test test cases
2006-03-25 | 5 | Finalizing test plan
Week #9 | 17.5
2006-03-19 | 5 | TA + Group meeting
~ | 12 | Unit test script / execution
2006-03-25 | 10 | dealing with video/mac issues
Week #10 | 27 |  | Total: | 141.5

## Dan Liu
Work Allocation Hours
Member: | Dan Liu
Date (dd/mm/yyyy) | Hours | Activity
2006-01-24 | 2 | Client Meeting & TA Meeting
| 2 | SRS 3.1 - 3.2 (rough draft)
Week #1: | 4
2006-01-31 | 1 | Pre-TA Meeting
| 1 | TA Meeting
2006-02-01 | 2 | SRS 3.1 - 3.2 (second draft)
| 4 | Project Plan
| 2 | Configuration of the entire SRS & Project Plan
Week #2: | 8
2006-02-07 | 2.5 | TA Meeting
2006-02-08 | 3 | SRS 3.1 - 3.2
2006-02-09 | 3 | SRS 3.2 & project plan
Week #3: | 7.5
2006-02-16 | 2 | GroupMeeting
2006-02-19 | 1 | SDD
Week #4: | 3
2006-02-21 | 1.5 | TA Meeting
2006-02-25 | 1 | Update SRS and SDD
Week #5 | 2.5
2006-02-28 | 1.5 | TA Meeting
2006-03-04 | 6.5 | Implementation
Week #6 | 8
2006-03-07 | 1.5 | TA Meeting
| 12 | Testing & SDD
Week #7 | 13.5
2006-03-12 | 10 | ad hoc testing
~ |  | installer wizard & cd autorun wizard
2006-03-18 | 2.5 | TA Meeting + filming
Week #8 | 12.5
2006-03-19 | 2.5 | TA + Group meeting
~ | 20 | Javadoc, CD installer, test script (unit test)
2006-03-25
Week #9 | 22.5
2006-03-26 | 5 | TA + Group meeting
~ | 13 | Javadoc, CD installer, test script (unit test)
2006-04-01
Week #10 | 18 |  | Total: | 99.5

## Wei Lin
Work Allocation Hours
Member: | Wei Lin
Date (dd/mm/yyyy) | Hours | Activity
2006-01-24 | 2 | Client Meeting & TA Meeting
Week #1: | 2
2006-01-31 | 1 | TA Meeting
2006-02-04 | 2 | SRS 1
2006-02-05 | 4 | SRS 1 & 6
Week #2: | 7
2006-02-07 | 1.5 | TA Meeting
2006-02-08 | 10 | Finalize SRS (revision)
Week #3: | 11.5
2006-02-16 | 2 | Group Meeting
2006-02-19 | 10 | Finalize SDD first draft
Week #4: | 12
2006-02-21 | 1.5 | TA Meeting
2006-02-24 | 10 | Finalize SDD final draft
Week #5 | 11.5
2006-02-28 | 1.5 | TA Meeting
2006-03-01 | 2.5 | Video Shooting
| 2 | Scripts
Week #6 | 6
2006-03-07 | 1.5 | TA Meeting
2006-03-09 | 2.5 | filiming
Week #6 | 4
2006-03-07 | 1.5 | TA Meeting
2006-03-09 | 2.5 | filiming
Week #7 | 9
2006-03-14 | 2 | filming
| 0.5 | TA Meeting
2006-03-17 | 5 | SDS
2006-03-18 | 1 | test plan - sec 6
Week #8 | 6
2006-03-29 | 2.5 | TA + Group meeting
~
2006-03-25
Week #9 | 2.5
2006-03-26 | 2.5 | TA + Group meeting
~ | 10 | user manual
2006-04-01
Week #10 | 12.5 |  | Total: | 84

## George Firican
Work Allocation Hours
Member: | George Firican
Date (dd/mm/yyyy) | Hours | Activity
2006-01-24 | 2 | Client Meeting & TA Meeting
| 2 | investigating programming language
| 4 | SRS 2 (rough draft)
Week #1: | 8
2006-01-31 | 3 | TA Meeting
| 1 | Gantt Graph & Project Plan
| 1 | Project Plan
| 1 | SRS 2
Week #2: | 6
2006-02-07 | 1.5 | TA Meeting
2006-02-09 | 4 | SRS 2 revision
| 0.5 | Gantt Graph & Project Plan revision
Week #3: | 6
2006-02-13 | 80 | Code:GUI,Video, PieChart, XML
~ | 10 | UI Class Diagram
2006-02-16 | 2 | Group Meeting
Week #4: | 92
2006-02-21 | 1.5 | TA Meeting
| 6 | Implementation
Week #5 | 7.5
2006-02-28 | 1.5 | TA Meeting
2006-03-03 | 35 | Implementation
Week #6 | 36.5
2006-03-05 | 55 | Implementation
~ | 10 | design
2006-03-11
Week #7 | 65
2006-03-12 | 63 | bug fixing
~ |  | tutorial video & design
2006-03-18 | 2.5 | TA meeting & filming
Week #8 | 65.5
2006-03-19 | 2.5 | TA + Group meeting
~ | 15 | 15 hours - fixing bugs & testing & Mac compatibility
2006-03-25
Week #9 | 17.5
2006-03-26 | 5 | TA + Group meeting
~ | 20 | regular testing and bug fixing, installer
| 4 | JUnit
2006-04-01 | 3 | code update
Week #10 | 32 |  | Total: | 336